## Overview
Bay — Phase 1 delivery tracker
Updated 8 October 2026 · implementation, data quality, and release evidence
Metric | Current value | Decision / release note
Completed implementation items | 15 | India location persistence, coordinate-only directions, catalog guardrails, map-space layout, and startup code splitting are complete. The Phase 1 feature set is usable for India, Melbourne, and the United States. One Melbourne source-accuracy finding remains deliberately open: segment-level rules must be re-imported against sign/bay coordinates before being presented as bay-specific.
Open accuracy items | 1
India catalog records checked | 2618
India cities in current catalog | 3
India published price records | 112
Automated tests passing | 80
Evidence: feature-tracker.pdf; test-1-findings.md; current source, test suite, production build, and catalog verifier.

## Delivery tracker
Phase 1 delivery register
Status is evidence-led: Complete means implemented and validated; Open means intentionally not represented as solved.
ID | Workstream | Requirement / issue | Status | Implementation or decision | Validation evidence | Updated
P1-01 | Location | Persist last chosen location and default home | Complete | Versioned local storage; first confirmed location becomes Home; Home and Work can be saved and recalled. | Saved-location unit + browser reload smoke test | 8 Oct 2026
P1-02 | Location | Do not reopen a different country after a slow or denied GPS request | Complete | Saved location takes precedence at startup; GPS only runs when no saved location exists. | App startup flow reviewed; saved-location tests | 8 Oct 2026
P1-03 | Onboarding | Remove country-list marketing from the location screen | Complete | Neutral copy and locale-aware country selector replace the Melbourne/India/USA banner. | Production build | 8 Oct 2026
P1-03b | Onboarding | Make city search work across the selected country without a state prerequisite | Complete | Country-level city search removes the alphabetical-state default that blocked Chennai/Bengaluru selection. | Chennai browser smoke test | 8 Oct 2026
P1-04 | Directions | Send drivers to the displayed Indian parking marker | Complete | One coordinate-only Google Maps driving URL builder replaces imported text/query destinations. | directions unit tests | 8 Oct 2026
P1-05 | India data | Only show usable, sourced India catalog rows | Complete | Client guard checks country, city bounds, source identity, public access, and price-source fields. | 2,618-row integrity audit | 8 Oct 2026
P1-06 | India data | Show published prices without inventing tariffs | Complete | Only exact operator-matched tariffs and source-backed price summaries are shown. | Catalog verifier | 26 Sep 2026
P1-07 | Performance | Avoid slow remote database calls for India/USA catalog searches | Complete | Regional catalogs are loaded directly; unused remote parking RPC calls are skipped. | Automated tests; production build | 8 Oct 2026
P1-08 | Mobile map | Keep a useful map viewport after filters are chosen | Complete | Map view is flex-sized to the remaining screen; filters remain collapsed by default. | Production build | 8 Oct 2026
P1-09 | Performance | Reduce startup payload and map loading time | Complete | Home, map, add-sign, guide, and activity screens are split into on-demand bundles. | Production build: main JS 295.5 kB | 8 Oct 2026
P1-10 | Availability | Keep live status separate from parking permission | Complete | Only fresh exact Melbourne sensor matches colour a bay; India uses mapped availability-on-arrival wording. | Existing availability and sensor tests | 26 Sep 2026
P1-11 | Data quality | Exact sensor-to-bay matching | Complete | Melbourne sensor display requires matching kerbside ID; unsafe legacy coordinate assignment is bypassed. | Test 1 finding #1 | 24 Sep 2026
P1-12 | Data quality | Crowd reports remain supplementary to sensors | Complete | Crowd and sensor observations are separated in status handling. | Test 1 finding #2 | 24 Sep 2026
P1-13 | Data quality | Import mixed Melbourne sign rules to the correct bay | Open | Known segment-wide loading-zone rule broadcast remains unsafe. Do not mark this bay-specific accuracy work complete until sign-coordinate import and audit land. | Test 1 finding #3 | Release blocker for that rule source
P1-14 | Parking areas | Separate facilities from individual bays | Complete | Parking areas use distinct P markers/details and never present capacity as a free-space count. | Catalog tests and current UI | 26 Sep 2026
P1-15 | Release hygiene | Maintain reproducible source/data record | Complete | Data manifest, stored source snapshots, tests, build checks, and this tracker provide release evidence. | verify_regional_catalogs.py | 8 Oct 2026

## India coverage
India parking coverage — deployed catalog
Snapshot collected 26 September 2026. Prices are only displayed where a published source was matched to that facility.
City | Total records | Parking areas / zones | Mapped bays | Price-backed records | Sources | Occupancy status
Chennai | 721 | 593 | 128 | 40 | OpenStreetMap; Chennai Metro Rail | No reusable current bay-sensor feed confirmed
Bengaluru | 1481 | 1379 | 102 | 70 | OpenStreetMap; Bengaluru Metro Rail | No reusable current bay-sensor feed confirmed
Hyderabad | 416 | 395 | 21 | 2 | OpenStreetMap | No reusable current bay-sensor feed confirmed
Validation on 8 October 2026: all 2,618 rows had valid city coordinates, source identity, public-access checks, and tariff-source checks.